## Base Guideline
# | Activities | Effort | Role
Test Initiation
1 | Functional Decomposition | If detailed Scope document is prepared 15% else 10% of Total planning effort. | BA
2 | Understanding the application under test |  | TE,BA,TL
3 | Inter Team Knowledge Transfer and understanding |  | TE,BA,TL
4 | Clarifications document preparation & review |  | TE,BA,TL
5 | Preparation and Review of Scope Document |  | BA
Test Planning
6 | Customer Quires/ Project documentation preparation & review | 5% of Project Management Effort | PM,TL
9 | Preparation of Test Cases | 15 Per Day | TE
10 | Review of Test Cases | 25% of Preparation | TL
11 | Preparation of Scenarios | 10 per day | BA
12 | Review of Scenarios | 25% of Preparation | BA
13 | Preparation of Activity/Run Plan | 10% of Test Cases Effort | BA
14 | Review of Activity/Run plan | 25% of Preparation | BA
17 | Preparation of Test Data | 20 Test Cases Per Day | TE
18 | Review of Test Data | 25% of Preparation | TL
19 | Rework on Testware | 10% of Preparation of Testware | TE
20 | Rework Review | 25% of Rework Effort | BA
21 | Preparation and Test Environment Ready report | 1 Person day | PM,TL
Test Execution
22 | Verification of Test Environment ready list | 1 Person day | TL
23 | Creation of test bed | 40% of test data Effort | TE
24 | Execute Test Cases. | 25 Cases per Day | TE
25 | Preparation of Defect Logs | 50% of Defect Log Review | TL
26 | Review of Defect logs | 10% of Execution Effort | TL
27 | Update the defect report | 50% of Defect Log Review | TL
28 | Status Reporting |  | PM,TL
Test Closure
29 | Closure document preparation | 3 Person days | TE / TL
30 | Project closure | 1 Person day | TE
31 | Archiving | 1 Person day | TL
Quality
32 | QMS related project Maintenance ( % of RoleTotal Effort) | 10% of Total TL Effort + 2 % of Total PM Effort + 3% of Total BA effort + 2% of Total TE effort | PM,TL,BA,TE
34 | Project Management Activity- 18% of the total project effort
1. Project budget, Schedule and plan preparation
2. Client Interaction and status reporting
3. Attending team meetings
4. Attending defect review meetings and reviewing defect reports
5. Review final defect report and Test Summary report

## Summary
Client First New - Tentative Effort Estimate
Functional Testing | Role |  |  |  | Person days | Person Months | % on Total Effort
Initiation | 0 | 1.4959 | 1.4959 | 8.9755 | 11.9673 | 0.59836 | #VALUE!
Planning | 16.2171 | 13.6392 | 22.5734 | 90.9382 | 143.368 | 7.1684 | #VALUE!
Execution | 4.9641 | 3.0568 | 3.344 | 37.62 | 48.9849 | 2.4492 | #VALUE!
Closure | 3 | 5.344 | 0 | 0 | 8.344 | 0.4172 | #VALUE!
Total 1 MD Effrot | 24.1812 | 23.5359 | 27.4134 | 137.5337 | 97 Days | 5 Months
Total in person months | 1.2091 | 1.1768 | 1.3707 | 6.8767 | #VALUE!
% age on Total Effort | #VALUE! | #VALUE! | #VALUE! | #VALUE!
Note on C5: Naren: 40% of project management effort has been assumed as planning and 60% as execution

## Effort
Sl.No. | Activity | Total Effort | Estimate in (Person Days)
|  |  | PM | TL | BA | TE
1 | Knowledge Transfer
2 | Functional decomposition
3 | Understanding of the application
| Test Initiation | 11.9673 | 0 | 1.4959 | 1.4959 | 8.9755
4 | Coustomer Quireis/ Documention preparation & Review | 5 | 2 | 2 | 1
5 | Preparation of Test Cases | 69.6667 |  |  |  | 69.6667
6 | Review of Test Cases | 17.4167 |  |  | 17.4167
7 | Preparation of test data | 8.36 |  |  |  | 8.36
8 | Review of Test Data | 2.09 |  |  | 2.09
9 | Preparation of Execution or Activity Plan | 4.6444 |  |  |  | 4.6444
10 | Review of Execution or Activity Plan | 1.1611 |  | 1.1611
11 | Re-work of Test Ware | 8.2671 |  |  |  | 8.2671
12 | Review of Re-work of testware | 3.0668 |  | 1 | 2.0668
13 | Prepare and Review of Zero-day checklist | 0
| Test Creation Planning | 119.6728 | 2 | 4.1611 | 22.5734 | 90.9382
| Initiation + Test Creation Planning | 131.6401 | 2 | 5.657 | 24.0694 | 99.9137
14 | Verifiy zero day check list | 0
15 | Creation of test bed | 5.18 |  | 1 |  | 4.18
Iteration I - Comprehensive
16 | Execute test cases | 33.44 |  |  |  | 33.44
17 | Review of Incident logs | 3.344 |  |  | 3.344
18 | Update the Incident report | 1.672 |  | 1.672
| Test Execution | 43.636 | 0 | 2.672 | 3.344 | 37.62
19 | Closure Mertics Preparation | 4.344 | 1 | 3.344
20 | Closure meeting | 2 | 1 | 1
21 | Archive project data (Project Closure Activties) | 2 | 1 | 1
| Test Closure | 8.344 | 3 | 5.344 | 0 | 0
| Execution + Closure | 45.964 | 3 | 5.344 | 0 | 37.62
| Project Management | 35.5208 | 7.1042 | 14.2083
| Total Person Days (Including Project Management) | 198.9165 | 12.1042 | 25.2093 | 24.0694 | 137.5337
| Total Person months | 9.9458 | 0.60521 | 1.2605 | 1.2035 | 6.8767
Note on D7: njad: 10% of Planning Effort.
Note on D32: njad: 20% of Planning & Execution
Note on F25: njad: 50% of Review effort.
Note on F27: njad: 10% of Test Exeution effort.
Note on G10: njad: 25% of Test Preparation
Note on G24: njad: 10% of Execution effort.
Note on H15: njad: 10% of TC, TD and AP preparation.
Note on H21: njad: 50% of TC Preparation.

## Calculator
EFFORT CALCULATOR (Man Day Effort)
Test Conditions
Test Cases | 836
Test Scripts | 83.6
Test Condition Preparation | No.s
Estimated per day | 40
Estimated no of days for preparation | 0
Test Cases Preparation | No.s
Estimated per day | 12
Estimated no of days for preparation | 69.6667
Test Data Preparation | No.s
Test Data Preparation per day | 100
Estimated no of days for Test Data preparation | 8.36
Test Execution or Activity Plan | No.s
Test Activity per Test Case | 180
Estimated number of days for Test Activity/Run Plan | 4.6444
Test Execution
Estimated test Cases per day | 25
Estimated number of days for Executing Test cases | 33.44
Note on D21: njad: 1/2 the Test Data Preparation Effort

## TC Count
Effort Estimation for Functional testing
Modules | Functions |  |  | Total Functions | Test Cases |  |  | Total
| Complex | Medium | Simple |  | Complex | Medium | Simple
CF | 40 | 34 | 21 | 95 | 480 | 272 | 84 | 836
Total | 40 | 34 | 21 | 95 | 480 | 272 | 84 | 836
Note on C3: Functions based on FS docs referred
Note on G3: 1 Complex function = 12 Test Cases 1 Medium function = 8 Test Cases 1 Simple function = 4 Test Cases

## Func Scope
Functions | Complex | Medium | Simple | Test Steps
Default Links available across screens
Log out |  |  | a
Log in |  |  | a
My Profile |  |  | a
Support |  |  | a
External Links |  |  | a
Create Call Report |  | a
Client Search (Advanced / Last Search) to verify the enittlements | a
Last Access Time |  |  | a
DB Logo |  |  | a
What's New |  |  |  |  | a
Since Last visit (not working as of now) Last 7 days (not working as of now) Past 30 days (not working as of now) |  | a
Print Page - on Each Screen - combinations will be taken | a
Page Help - On each screen |  | a
New Final Call Reports
Content & Layout |  | a
Add Call report (Same Screen as Edit below) On New Final Call Reports Data Tab On New Deals Data Tab etc.. | a
View More/less Call reports (Min & Max Button also) On New Final Call Reports Data Tab On New Deals Data Tab etc… | a
Date Link (Same for My Actions- New Call reports ) 1. Edit / Clone / Close (On top & bottom of page) Edit - a. Edit Some part of the data (Client/ Participants) - Client Information - General Information - Call report Information - To do Actions - Add To do / Actions (link not working) - Attachments - Add Documents/ Delete docs - New Screen to Add attachements (Browse -select file) - add / cancel b. save Draft & continue c. Save Draft & Close d. Cancel e. Save Final f. Print page 2. Previous / Next Click 3. Clone - not woking at the moment | a
- To do Actions - Add To do / Actions (link not work | a
- Attachments - Add Documents/ Delete docs - New Screen to Add attachements (Browse -select file) - add / cancel | a
b. save Draft & continue |  | a
c. Save Draft & Close |  | a
d. Cancel | a
e. Save Final | a
3. Clone - not woking at the moment | a
Creater Link - not working as of now | a
Help On New Final Call Reports Data Tab On New Deals Data Tab |  | a
New Deals
Pending/ Closed - layout
Date Link - same for Pending & Closed 1. Previous / Next 2. Modify/Delete/Close - Modify a. Cancel/ Save b. Client info c. Parent Infor d. Deal Infor e. products - Add products (not working as of now) f. Description g. Deal Team - Add Deal team - Multi Banker Look up Screen h. Other Deal principals - Add other Deal principals (not working) i. To do Actions - Add To do Actions (not working as of now) | a
e. products - Add products (not working as of now) | a
g. Deal Team - Add Deal team - Multi Banker Look up Screen | a
h. Other Deal principals - Add other Deal principals (not working) | a
My Actions
New Draft Call reports - same as New Final call reports - layout |  | a
Open to do's
Filter - To Show To do's - By Me/For Me |  | a
Filter - To Show To do's - Next 7/14/30 days |  | a
Date Link - create new call report (Not working) - create new Deal report (Not working) - create new client contact (Not working) - View Associated Record (Not working) - Modify - new small screen with cancel / Save - close | a
Author Link (not working) Resposible Link (Not working) |  | a
Open Maturities
Date Link - Settle Maturity (not working) - Start ELKAS (not working) - Close | a | a
Filter - Show - Mine - Teams - Regions | a
Filter - Show - Next 7/14/30 days | a
Birthdays
- layout - Contact Name Link - Client Link |  | a
Filter - Show - Next 7/30 days - last week | a
My Clients
1. Layout 2. List of Clients - (Link) - - Opens Same screen as Workbench Coverage & Contacts 3. Delete icon for each client 4. SIB/SB/Main RM Link | a | a | a
Add Client - not working | a
Workbench
Client Tier - mentioned on this screen |  |  | a
Workbench Help (not working) |  |  | a
Add To my Client List (not working) |  | a
Coverage & Contacts
Client Service Team - View Entire Client Service Team - View All CST Roles - View Just Core CST - Modify CST - Role Link (not working) | a | a | a
Equity Reseach & PCAM - name link (not working) |  | a
Client Contacts - View More Client Contacts - View Board profile (not working) - Role Link take to Role Details On click of Client Link - new screen - Delete Contact - Close Contact - Modify - Merge Detail Information 1 Contact Details a. Current Role - Role Link - goes to Role details - Delete / Modify Link on each Contact (not working) - Add Link (not working) b. Past Employment - Role Link - goes to Role details - Delete / Modify Link on each Contact (not working) - Add Link (not working) c. other activities d. Education e. Achievements 2. Contact Communication 3. Mkting Materials 4. Role Details - Add / Modify / Delete - Change Role thru combo - Modify/ Merge Button present same as on Contact details - will take user to the first Tab - Contact details in modify mode. | a | a | a
4. Role Details - Add / Modify / Delete - Change Role thru combo - Modify/ Merge Button present same as on Contact details - will take user to the first Tab - Contact details in modify mode. | a | a | a
3. Mkting Materials | a
2. Contact Communication - add Call reports | a
Revenues & Wallets
Data from the Revenue and Planning Module
Filter - All Units - some units - More Units View more / Less | a | a
Deals
Pending - Last UpDate Link (same as on row 33 - same screen) | a | a | a
Closed - Last UpDate Link (same as on row 33 - same screen) | a | a | a
View more Deals |  | a
Add to My Client list |  |  | a
Client Interactions
Call reports
Date Link - same screen as on row 19 | a
View More / less Call Reports |  | a
Creator - (not working) | a
Add call report (not working) |  | a
To Do's & workflows
View More/Less To do's |  |  | a
Date Link - View Associated Record (Not working) - Modify - new small screen with cancel / Save - workbench help Link - close | a | a | a
Author Link |  | a
Responsible Link |  | a
Help |  |  | a
Credit- not part of Phase 1
Product & Maturities
Maturities 1. Open a. product Link - Client Info/ Maturity info - Start ELKAS (not working) what is this also? - Settle Maturity (not working) - Close | a | a | a
2. Closed a. product Link - Client Info/ Maturity info - Start ELKAS (not working) what is this also? - Settle Maturity (not working) - Close | a | a | a
3. View More Maturities |  | a
Products / Accounts - View more products/ accounts Tabs available for various products categories - on click products that category are listed out ... - Loans & deposits - FX Cash - Derivatives - BOE - LC -Securities | a | a
Spend
mkting materials spend summary and details | a
Static Data
Client Static Data
- Modify - Cancel / Save modifications - can modify Address - new screen Address Look Up - Create and Add new Address - Cancel - Select (from the options available to the user) - Client website link - Alias - Enable Workbench (not working)
- Cancel / Save modifications | a
- can modify Address - new screen Address Look Up - Create and Add new Address - Cancel - Select (from the options available to the user) | a
- Client website link |  | a
- Alias |  | a
- Enable Workbench (not working) | a
| 40 | 34 | 21 | 0 | 0